## FCO -> Instance Map
FCO # | Title | Triage | PRIMARY Unit (best guess) - serial | Primary Unit (label) | Applicable Units | Assignment Confidence | Spawns per-Instance FC | Basis for guess | GitLab confirmation | Reassignable
FCO-2025-001 | DHL DFW Excess cable cover (R2) | ECR | IN001024355007 | Unit 7 (DHL Cell1/Lane8) | Units 7,8 | Low | No | R2 cable work at DHL DFW; primary=first DHL cell. Fleet-ish. | DHL DFW = units 7&8 confirmed shipped (proj 63073439). | Yes - tracked (Version log); requires reason on change
FCO-2025-002 | DHL DFW VPA valve 30-45deg R2 | ECR | IN001024355007 | Unit 7 (DHL Cell1/Lane8) | Units 7,8 | Low | No | R2 valve at DHL DFW; primary=first DHL cell. | DHL DFW = units 7&8. | Yes - tracked (Version log); requires reason on change
FCO-2025-003 | Pick-2 Bumper UPS-WP | FCO | IN002024257003 | Unit 3 (WP 7C) | Units 3,4 | Low | No | Worldport pick-2 guard; canceled. WP units. | WP = units 3,4. | Yes - tracked (Version log); requires reason on change
FCO-2025-005 | Beth SAI2 Assembly/Install process | ECR | IN002024267005 | Unit 5 (Beth 2-1) | Units 5,6 | Med | No | SAI2 = Beth 2-series install; primary Unit 5. | Beth 2-1/2-2 = units 5,6. | Yes - tracked (Version log); requires reason on change
FCO-2025-006 | Brush Joiner Filler Guides WP 6C/7C | FCO | IN002024257004 | Unit 4 (WP 6C) | Units 4,3 | Med | No | Named lanes 6C&7C; rejected. | WP 6C/7C = units 4,3. | Yes - tracked (Version log); requires reason on change
FCO-2025-007 | Justify MDR rollers non-motor WP 6C/7C | ECR | IN002024257003 | Unit 3 (WP 7C) | Units 3,4 | High | YES | EC-25-0223 COMPLETED on WP 6C&7C -> spawn per-unit FC on units 3 AND 4. | WP 6C/7C = units 3,4; EC completed. | Yes - tracked (Version log); requires reason on change
FCO-2025-008 | Replace CMOS battery Beth SAI2-2 IPC2 | FCO | IN002024267006 | Unit 6 (Beth 2-2) | Unit 6 | High | No | Explicit Beth SAI2-2 = Unit 6; rejected. | Beth 2-2 = unit 6. | Yes - tracked (Version log); requires reason on change
FCO-2025-009 | Hose Changes DHL7&8/Onexia/Beth2-1&2-2 | ECR | IN001024355008 | Unit 8 (DHL Cell2/Lane7) | Units 8,7,5,6 + Onexia | Med | No | Multi-site; primary=first listed (DHL lane7=Unit8). Onexia untracked. | DHL7=Unit8, DHL8=Unit7, Beth2-1/2=5/6. | Yes - tracked (Version log); requires reason on change
FCO-2025-010 | i1 lights straight down after OD retrofit | ECR | IN001024355007 | Units 7 & 8 (OD-retrofit units) | Units 7,8 (OD units) | Med (confirmed) | YES (units 7,8) | ECR = 'V1 to V2 Retrofit / OD camera retrofit' doc; site 'All v2 i1' = OD-equipped units. Tracker OD col: units 7,8 (+ untracked v2/OD cells). | CONFIRMED via linked retrofit doc + tracker OD column. Also applies to untracked v2/OD cells (WP Primary-3). | Yes - tracked (Version log); requires reason on change
FCO-2025-011 | Beth2-1 Sidepan cutouts | FCO | IN002024267005 | Unit 5 (Beth 2-1) | Unit 5 | High | No | Explicit Beth 2-1 = Unit 5; rejected. | Beth 2-1 = unit 5. | Yes - tracked (Version log); requires reason on change
FCO-2025-012 | v2 Gripper Retrofit PSI spec change | ECR | IN001024355007 | Unit 7 (v2 gripper) | Units 7,8 (Gripper HW2.0) | Med | No | v2 grippers = HW2.0 units (7,8 per tracker). In progress. | Gripper HW 2.0 = units 7,8. | Yes - tracked (Version log); requires reason on change
FCO-2025-013 | Hose Changes Onexia Cell 2 | ECR |  | Onexia (untracked) | Onexia | High | No | Onexia unit NOT in tracker -> organic Instance creation. | Onexia not in fleet tracker. | Yes - tracked (Version log); requires reason on change
FCO-2026-014 | Removal of Pump Enclosure Sound Insulation | ECR | IN001024355007 | Unit 7 (nominal) | Fleet: Beth/WP/DHL | Low | No | Over-temp on a trip; fleet-wide ECR. Nominal primary only. | Fleet-wide. | Yes - tracked (Version log); requires reason on change
FCO-2026-015 | Spacer to prevent R2 vac valve rotating | ECR | IN002024267005 | Unit 5 (nominal) | Fleet: All InductOne | Low | No | Fleet-wide ECR (Onexia-designed spacer). Nominal primary. | Fleet-wide. | Yes - tracked (Version log); requires reason on change
FCO-2026-016 | Fan only part number request | ECR | IN001024262001 | Unit 1 (nominal) | Fleet: All | Low | No | Part-number request; no single origin unit. Nominal primary. | Fleet/catalog. | Yes - tracked (Version log); requires reason on change
FCO-2026-017 | Canister Filter part number request | ECR | IN001024262001 | Unit 1 (nominal) | Fleet: All | Low | No | Part-number request; no single origin unit. Nominal primary. | Fleet/catalog. | Yes - tracked (Version log); requires reason on change
FCO-2026-018 | Beth 1-2 Field Test (grippers & vac hose) | FCO | IN001024262002 | Unit 2 (Beth 1-2) | Unit 2 | High | pending | Explicit Beth cell 1-2 = Unit 2. (Possibly Deviation.) | Beth 1-2 = unit 2. | Yes - tracked (Version log); requires reason on change
FCO-2026-019 | Fiber Network Install UPS Worldport | FCO | (untracked - organic) | WP Primary-3 cell (loc WP-C-3-2/3-3) - pending serial | WP P3 cells 3-2, 3-3 (NOT tracker units 3/4) | High (site) / organic (unit) | pending (organic Instance) | GitLab WI #170 (proj 57192442): fiber->Ethernet A-B 1783-ETAP1F at WP Primary-3 IPC during Feb-2026 commissioning of cells 3-2/3-3. These are NOT tracker units 3/4 (=P6/P7 lanes 6C/7C). Locations now seeded (WP-C-3-2/3-3). | CONFIRMED. REVEALS untracked Worldport Primary-3 cells (3-2 Onexia, 3-3) absent from the 10-unit tracker. | Yes - tracked (Version log); requires reason on change
FCO-2026-020 | UPS Beth 2-2 Electrical Panel upgrade | FCO | IN002024267006 | Unit 6 (Beth 2-2) | Unit 6 | High | pending | Explicit Beth 2-2 = Unit 6; Rev E contactor retrofit. | Beth 2-2 = unit 6. | Yes - tracked (Version log); requires reason on change