## README
SUP-FCO-R01 — Field Change Order (FCO) Register
Plus One Robotics — InductOne Configuration Status Accounting
Document | SUP-FCO-R01
Schema version | 2.0 (Draft — pending release via EC-YY-NNNN)
Classification | Internal — Plus One Robotics
Owner | Operations Engineering (Michael King)
Operating maintainer | Technical Operations, with Operations Engineering
Governing documents | OPS-CSA-PLN-001 §7 / §11; OPS-FCO-T01; OPS-FCO-T02; OPS-CFG-DEV-01
How this register works
This file releases the register SCHEMA as a controlled document. The OPERATING register is a single
record instance maintained at: SharePoint > TechnicalOperations > Field Deployment Resources > General > FCO (Field Change Orders) > FCO_Index.xlsx
The operating instance carries this schema version in its header. Schema changes are made through the
Engineering Change process (ECR > ECO > ECN) and migrated into the operating instance.
Flow: intake via the POR Field Change / Deviation intake form (JotForm) > Operations Engineering
triage (FCO / Deviation / ECR) > register here > disposition on OPS-FCO-T01/T02 > implement >
completion incl. ERPNext as-maintained update > close. Every intake submission gets a row, including
rows triaged to Deviation or ECR (their execution is recorded in their own instruments).
Historical numbering: JotForm Change No 1-20 backfilled 2026-07-13 as FCO-YYYY-0NN (original numbers
preserved; Change No 4 was never issued in the source export). New rows continue from FCO-2026-021.
Column definitions
Column | Definition | Example
FCO # | Register identifier FCO-YYYY-### (year of submission + intake Change No; historical numbering preserved). | FCO-2025-007
Date Raised | Date the request was submitted (intake form date). | 2025-10-22
Requester | Person who raised the request. | P. Gomez
Intake Ref (Submission ID / Link) | JotForm Change No / submission reference; blank if raised directly by Operations Engineering. | JotForm Change No 7
Customer / Project | Site, project, or customer the change applies to. | UPS Worldport
IND-#### Serial(s) / Location(s) | Machine serial(s) and/or cell/location affected. Serials required before disposition of new FCOs. | IND-0042 / Beth cell 2-2
Change Summary | One-line description of the change. | Justify MDR rollers to non-motor side
Triage Outcome | Operations Engineering triage: FCO (one-time post-shipment), Deviation (pre-delivery departure, OPS-CFG-DEV-01), or ECR (design change raised through the Engineering Change process). | ECR
Reference (ECR / Epic / Ticket) | EC number, GitLab ECR/Epic, or issue link that carries the change. | EC-25-203
Safety / Regulatory (Y/N) | Whether the change has safety or regulatory impact. | N
Disposition | Approved / Conditional / Rejected, recorded on OPS-FCO-T01 or T02 (blank while pending or when routed to ECR). | Approved
Disposition Date | Date the disposition was made. | 2026-07-15
Implemented Date | Date the change was completed in the field. | 2026-07-20
As-Maintained Updated in ERPNext | Y once the unit's as-maintained record reflects the change; N flags pending backfill; N/A for rejected or design-side rows. | Y
Post-Change Test | Pass / Fail / N/A per the FCO completion record. | Pass
Status | Open until implemented, verified, and recorded; then Closed. | Closed
Closed Date | Date the register row was closed. | 2026-07-21
Notes | Working notes: routing history, cancellation reasons, cross-references. | Consolidated into FCO-2025-009's ECR
Revision history
Rev | Summary | Date / Author
1.0 | Original FCO Index provided to Technical Operations. | 2025-04-23 / M. King
2.0 | Schema expanded for CSA integration: intake reference, IND serials, triage outcome, ECR/Epic reference, safety flag, disposition and completion tracking, notes. Historical JotForm submissions (Change No 1-20, 19 records) backfilled into the operating instance. Released with the CSA controlled document set. | 2026-07-13 / Operations Engineering

## FCO Register
FCO Register — SUP-FCO-R01
OPERATING REGISTER OF RECORD — instance of controlled schema SUP-FCO-R01 v2.0.
Location: SharePoint > TechnicalOperations > Field Deployment Resources > General > FCO (Field Change Orders) > FCO_Index.xlsx ¦ Schema changes arrive via the Engineering Change process (ECR > ECO > ECN).
Intake: POR Field Change / Deviation intake form (JotForm) > Operations Engineering triage > this register. See README for column definitions.
FCO # | Date Raised | Requester | Intake Ref (Submission ID / Link) | Customer / Project | IND-#### Serial(s) / Location(s) | Change Summary | Triage Outcome | Reference (ECR / Epic / Ticket) | Safety / Regulatory (Y/N) | Disposition | Disposition Date | Implemented Date | As-Maintained Updated in ERPNext | Post-Change Test | Status | Closed Date | Notes
FCO-2025-001 | 2025-09-05 | Gilbert Bailey | JotForm Change No 1 | DHL Dallas, UPS. InductOne |  | DHL DFW Excess cable cover | ECR | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4323 ¦ https://gitlab.com/groups/plusone-robotics/product/-/work_items/846. ¦ https://gitlab.com/plusone-robotics/operations/project_manager/dhl-north-america/dhl-inductone-dallas/dhl-dfw/-/issues/67 |  |  |  |  | N/A |  | Open |  | Routed to ECR (created 2025-12-22; Epic 2025-12-23). [Source note: ecr created 12/22/25. epic created 12/23/25.]
FCO-2025-002 | 2025-09-05 | Gilbert Bailey | JotForm Change No 2 | DHL Dallas, UPS. InductOne |  | DHL DFW Install VPA valve at 30-45 degrees for R2 | ECR | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4324 ¦ https://gitlab.com/groups/plusone-robotics/product/-/work_items/847 ¦ https://gitlab.com/plusone-robotics/operations/project_manager/dhl-north-america/dhl-inductone-dallas/dhl-dfw/-/issues/70 |  |  |  |  | N/A |  | Open |  | Routed to ECR (created 2025-12-22; Epic 2025-12-23). [Source note: ecr created 12/22/25; epic created 12/23/25]
FCO-2025-003 | 2025-09-09 | Wayne Kirk | JotForm Change No 3 | UPS, Workdport, V2 | Worldport (V2 pick-2) | Pick-2 Bumper for UPS-WP | FCO | https://gitlab.com/plusone-robotics/operations/project_manager/ups/worldport-inductone/-/issues/147 |  |  |  |  | N/A |  | Closed |  | Canceled — obsolete: new conveyors with OD sensors do not have the ride-along issue. [Source note: new conveyors w OD sensors do not have these bumpers.]
FCO-2025-005 | 2025-10-01 | James Nelson | JotForm Change No 5 | Bethlehem SAI2, unclear future implications | Bethlehem SAI2 | i1 Beth SAI2 Assembly/Install process | ECR | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4325 ¦ https://gitlab.com/groups/plusone-robotics/product/-/work_items/848 ¦ https://gitlab.com/plusone-robotics/operations/project_manager/ups/bethlehem-inductone/-/issues/134 |  |  |  |  | N/A |  | Open |  | Routed to ECR (created 2025-12-22; Epic 2025-12-23). [Source note: ecr created 12/22/25; epic created 12/23/25]
FCO-2025-006 | 2025-10-22 | Patty Gomez | JotForm Change No 6 | UPS, Worldport, V2, Lanes 6C and 7C. | Worldport Lanes 6C/7C | "Conveyor Brush Joiner" Filler Guides | FCO | https://gitlab.com/plusone-robotics/operations/project_manager/ups/worldport-inductone/-/issues/164#note_2786734678 |  | Rejected |  |  | N/A |  | Closed |  | Denied — no ECR needed. [Source note: Cancel this , no ecr needed]
FCO-2025-007 | 2025-10-22 | Patty Gomez | JotForm Change No 7 | UPS, Worldport, V2, Lanes 6C and 7C. | Worldport Lanes 6C/7C | Justify MDR rollers to non-motor side of conveyor. | ECR | EC-25-203 ¦ https://plusonerobotics.sharepoint.com/:w:/r/sites/PlusOneDocumentation/POR TECHNICAL PUBLICATIONS LIBRARY/InductOne/V1 to V2 Retrofit Instructions/Conveyor Powered Roller Adjustment.docx?d=wd8846c11240b43d9ae0c7b463f8ea334&csf=1&web=1&e=DkbvbG ¦ https://gitlab.com/plusone-robotics/operations/project_manager/ups/worldport-inductone/-/issues/164#note_2786734678 |  | Approved |  |  | N |  | Closed |  | Completed as EC-25-203 (physical change on fielded units — ERPNext as-maintained backfill pending). [Source note: EC-25-203; needs to be made into ECR to added to assembly print.]
FCO-2025-008 | 2025-11-06 | James Nelson | JotForm Change No 8 | UPS Bethlehem SAI 2-2 | Beth SAI2-2 IPC2 | Replace CMOS battery Beth SAI2-2 IPC2 CR2032 | FCO |  |  | Rejected |  |  | N/A |  | Closed |  | Denied — to be addressed in manufacturing process; ECR not needed. [Source note: complete during manuf process? ECR not needed.]
FCO-2025-009 | 2025-11-06 | James Nelson | JotForm Change No 9 | All i1 | All i1 (multiple cells) | Hose Changes at DHL Lane7 and 8, Onexia, Bethlehem SAI2-1 and Bethlehem SAI2-2 | ECR | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4326 ¦ https://gitlab.com/groups/plusone-robotics/product/-/work_items/849 | [6 empty] | Open |  | Routed to ECR (created 2025-12-22); documents field hose lengths. [Source note: ecr created 12/22/25 per Shaun's request to validate if one is ready for released. epic created 12/23/25]
FCO-2025-010 | 2025-11-07 | James Nelson | JotForm Change No 10 | All v2 i1, unclear if this is noted in the design documentat | All v2 i1 | i1 lights oriented straight down after OD retrofit | ECR | https://plusonerobotics.sharepoint.com/:w:/r/sites/PlusOneDocumentation/POR%20TECHNICAL%20PUBLICATIONS%20LIBRARY/InductOne/V1%20to%20V2%20Retrofit%20Instructions/OD%20camera%20retrofit%20Instructions.docx?d=we09c8bf69139431bbc70134f0989d833&csf=1&web=1&e=c48Uvq |  | Approved |  |  | N |  | Closed |  | ECR completed (lights reoriented on fielded units — as-maintained backfill pending).
FCO-2025-011 | 2025-11-10 | James Nelson | JotForm Change No 11 | UPS Beth SAI2-1 | Beth SAI2-1 | Beth2-1 Sidepan cutouts | FCO |  |  | Rejected |  |  | N/A |  | Closed |  | Denied — ECR not needed (source export ECR-status field inconsistent; verify).
FCO-2025-012 | 2025-11-13 | Nathaniel Pantuso | JotForm Change No 12 | All InductOne with v2 grippers | All v2-gripper units | v2 Gripper Retrofit - PSI specification change | ECR | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4327 ¦ https://gitlab.com/groups/plusone-robotics/product/-/work_items/850 | [6 empty] | Open |  | Routed to ECR (created 2025-12-22) — PSI spec 60→70. [Source note: ecr created 12/22/25 per Shaun's request to validate if one is in progress. epic created 12/23/25]
FCO-2025-013 | 2025-12-01 | James Nelson | JotForm Change No 13 | Onexia Cell 2, repeat as needed | Onexia Cell 2 | Hose Changes at Onexia Cell 2 | ECR | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4326 ¦ https://gitlab.com/plusone-robotics/operations/project_manager/builders/onexia/-/issues/3#note_2925543502 | [6 empty] | Open |  | Consolidated into FCO-2025-009's ECR (2025-12-22). [Source note: added to item 8 ecr 12/22/25]
FCO-2026-014 | 2026-01-07 | Wayne Kirk | JotForm Change No 14 | UPS Bethlehem, UPS Worldport, future UPS sites, DHL DFW, fut | UPS Bethlehem / Worldport | Removal of Pump Enclosure Sound Insulation | ECR | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4342 | [6 empty] | Open |  | ECR submitted 2026-01-08. [Source note: ecr submitted 1/8/26.]
FCO-2026-015 | 2026-02-02 | Patty Gomez | JotForm Change No 15 | All InductOne | All InductOne | Spacer to prevent R2 vac valve from rottatin | ECR | https://gitlab.com/groups/plusone-robotics/product/-/epics/861 | [6 empty] | Open |  | ECR submitted 2026-01-21 (Onexia-designed spacer). [Source note: ecr submitted 1/21/26.]
FCO-2026-016 | 2026-02-02 | Patty Gomez | JotForm Change No 16 | All InductOne | All InductOne | Fan only part number request | ECR | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4365 | [6 empty] | Open |  | ECR submitted 2026-02-02 (fan-only part number). [Source note: ecr submitted 2/2/26]
FCO-2026-017 | 2026-02-02 | Patty Gomez | JotForm Change No 17 | All InductOne | All InductOne | Canister Filter part number request | ECR | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4366 | [6 empty] | Open |  | ECR submitted 2026-02-02 (filter-element part number). [Source note: ecr submitted 2/2/26.]
FCO-2026-018 | 2026-04-06 | Jason Minica | JotForm Change No 18 | UPS Beth, cell 1-2 | Beth cell 1-2 (serial TBD) | Beth 1-2 Field Test (grippers and vacuum hose) | FCO | https://gitlab.com/groups/plusone-robotics/product/-/work_items/915 | [6 empty] | Open |  | Field test: redesigned grippers + two-piece vacuum hoses.
FCO-2026-019 | 2026-07-08 | Christina Gomez-Terry | JotForm Change No 19 | InductOne-WP UPS | UPS Worldport IPC panel (serial TBD) | Fiber Network Install | FCO | https://gitlab.com/plusone-robotics/operations/project_manager/ups/worldport-inductone/-/work_items/170 |  |  |  |  | N |  | Open |  | Change already implemented in field (retroactive record) — fiber run + AB switch by UPS/Alliant/Delta.
FCO-2026-020 | 2026-07-13 | Gilberto Bailey | JotForm Change No 20 | UPS | Beth cell 2-2 (serial TBD) | UPS Beth 2-2 Electrical Panel upgrade | FCO | https://gitlab.com/plusone-robotics/operations/project_manager/ups/bethlehem-inductone/-/work_items/151. https://gitlab.com/plusone-robotics/product/hardware-engineering/robotic-induction-cells/inductone-dual-arm-induction/inductone-v2.0/-/work_items/296 | [6 empty] | Open |  | Retrofit of Rev E contactor change onto fielded unit; design side already in Rev E.