## Sheet1
Submission Date | Flow Status | Change No | Date | Change Requestor | Email | Department | Role | Title of Field Change Order | Description of proposed change in plain English: | Benefit/Reason for change: | What site(s), project(s), or customer does this apply to? | Do you expect this to be a one-time fix, or repeated across sites? | Estimated Customer Downtime hours | Estimated Labor Hours | Part(s) Cost ($) | Who can implement this field change? | Tools / Documents Needed | Relevant issue tracker link or ticket: | Attachments | Submittal Date | Approver Email | ECR Link | ECR Status | Epic link | Notes
Sep 5, 2025 | In Progress | 1 | Sep 5, 2025 | Gilbert Bailey | gilbert.bailey@plusonerobotics.com | Operations | Sr. Systems Engineer | DHL DFW Excess cable cover | A 27g tote was installed to organize and cover the multiple excess cables, which were spooled at the skid because of their extra length. A hole was cut in the back of the tote to reorganize the cables without having to disconnect them. https://www.homedepot.com/pep/HDX-27-Gal-Tough-Storage-Tote-in-Black-and-Yellow-999-27G-HDX/327528802 | To conceal and manage multiple excess cable spools at the skid, ensuring a cleaner layout and minimizing potential safety risks | DHL Dallas, UPS. InductOne | Multiple sites for a specific project application | 0 | 1 | 10 | Anyone | Hot knife cutter should work best. I used cutting pliers and scissors that I had in hand, but it was not easy due the tote hard plastic material breaking. | https://gitlab.com/plusone-robotics/operations/project_manager/dhl-north-america/dhl-inductone-dallas/dhl-dfw/-/issues/67 | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6329172988762150969/Media.jpg https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6329172988762150969/shared%20image.jpg | Sep 5, 2025 | patty.gomez@plusonerobotics.com | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4323 | In Progress | https://gitlab.com/groups/plusone-robotics/product/-/work_items/846. | ecr created 12/22/25. epic created 12/23/25.
Sep 5, 2025 | In Progress | 2 | Sep 5, 2025 | Gilbert Bailey | gilbert.bailey@plusonerobotics.com | Operations | Sr. Systems Engineer | DHL DFW Install VPA valve at 30-45 degrees for R2 | Install the VPA valve in R2 at 30-45 degrees, replacing the previous 0-degree orientation | Protection of the VPA Valve avoids knocking off the filter. | DHL Dallas, UPS. InductOne | Multiple sites for a specific project application | 0 | 0.5 | 0 | Anyone | Can be adjusted by hand. | https://gitlab.com/plusone-robotics/operations/project_manager/dhl-north-america/dhl-inductone-dallas/dhl-dfw/-/issues/70 | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6329206018763590601/20250717_055628_resized.jpg https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6329206018763590601/20250717_060919_resized.jpg | Sep 5, 2025 | patty.gomez@plusonerobotics.com | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4324 | In Progress | https://gitlab.com/groups/plusone-robotics/product/-/work_items/847 | ecr created 12/22/25; epic created 12/23/25
Sep 9, 2025 | Canceled | 3 | Sep 9, 2025 | Wayne Kirk | wayne.kirk@plusonerobotics.com | Sales | Principal Solutions Architect | Pick-2 Bumper for UPS-WP | The V1 InductOne units at Worldport had a bumper added as a test to the pick-2 guard to keep parcels from standing up along the side and rendering them unpickable due to reach issues. This seemed to solve the problem. | It helps knock down parcels that ride along the guard of the pick conveyors and then get rejected due to them being unreachable. | UPS, Workdport, V2 | One-time for a specific site | 2 | 2 | 250 | Technician | Drawings, drills, vacuum, wrench assortment. | https://gitlab.com/plusone-robotics/operations/project_manager/ups/worldport-inductone/-/issues/147 | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6332367142212016387/WP-Pick-2_Bumper2.jpg https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6332367142212016387/Image%20%288%29.jpg | Sep 9, 2025 | patty.gomez@plusonerobotics.com |  | Cancelled |  | new conveyors w OD sensors do not have these bumpers.
Oct 1, 2025 | In Progress | 5 | Oct 1, 2025 | James Nelson | james.nelson@plusonerobotics.com | Operations | Systems Engineer | i1 Beth SAI2 Assembly/Install process | Boom lift on-site does not have the capacity to lift the frame at its current weight and deliver it to the far side of the sorter. Deviation is to dismount the robot mechanical units (92kg total) from the frame prior to install, then reinstall after frame is set. | System can actually be installed | Bethlehem SAI2, unclear future implications | One-time for a specific site | 0 | 4 | 0 | Installer contractor, Robot Lead, Mech Assy Lead | * LR-10 mech unit frame dwg for torque specs in remounting * Hose routing dwg for dresspack uninstall and reinstall * Metric Allen Key bit with torque wrench. | https://gitlab.com/plusone-robotics/operations/project_manager/ups/bethlehem-inductone/-/issues/134 |  | Oct 1, 2025 | patty.gomez@plusonerobotics.com | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4325 | In Progress | https://gitlab.com/groups/plusone-robotics/product/-/work_items/848 | ecr created 12/22/25; epic created 12/23/25
Oct 22, 2025 | Denied | 6 | Oct 21, 2025 | Patty Gomez | patty.gomez@plusonerobotics.com | Customer Support | Group Lead | "Conveyor Brush Joiner" Filler Guides | - Remove brush guard brackets in affected zones and install 3D printed pieces. Reattach. - Tools needed: M7 socket, M2.5 allen - 6 total brush guards (1611-027-1201) installed per Pick-1 belt, 3 on each side in the first 3 positions. SIDE NOTE: Lane 7 had a missing metal brush mount right at the entrance into Pick-1. A partial length of filler piece (cut down from original length) was added in its place to prevent infeed to Pick-1 parcel snags. | Installing these filler guides/3D printed pieces helps packages not get caught on the original brush mounts. Evidence has shown only these first 3 positions have issues with package catches, but the customer may request more be installed along the conveyors. | UPS, Worldport, V2, Lanes 6C and 7C. | All future deployments for this application type | 1 | 1 | 250 | Technician | - Tools needed: M7 socket, M2.5 allen - Required number of 3D printed filler pieces (minimum 6 per cell), PN: 1611-027-1201 | https://gitlab.com/plusone-robotics/operations/project_manager/ups/worldport-inductone/-/issues/164#note_2786734678 | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6369570792217338475/Lane6C-Pick1.jpg https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6369570792217338475/Lane7C-Pick1_MissingBracketFiller.jpg https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6369570792217338475/1611-027-1201.jpg | Oct 21, 2025 | patty.gomez@plusonerobotics.com |  | Cancelled |  | Cancel this , no ecr needed
Oct 22, 2025 | Complete | 7 | Oct 22, 2025 | Patty Gomez | patty.gomez@plusonerobotics.com | Customer Support | Group Lead | Justify MDR rollers to non-motor side of conveyor. | - MDR is loosened, shifted fully to non-motor side, and retightened. - Tools: M10 socket, flat-head screw driver - Loosen motor-side retaining bracket and shove roller fully to opposite end to prevent pop-out issue that has been observed | The spring-loaded shaft (non-motor) works its way inside of the roller and does not reset itself eventually leading to the shaft becoming disengaged from the conveyor side rail. This dislodges the roller from its seated position leading to increased wear and possibly decreased performance. | UPS, Worldport, V2, Lanes 6C and 7C. | All future deployments for this application type | 3 | 3 | 0 | Technician | - See attached released document - Tools: M10 socket, flat-head screw driver | https://gitlab.com/plusone-robotics/operations/project_manager/ups/worldport-inductone/-/issues/164#note_2786734678 | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6369588792211292714/MDR-OutOfPosition.jpg https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6369588792211292714/Conveyor%20Powered%20Roller%20Adjustment.pdf | Oct 22, 2025 | patty.gomez@plusonerobotics.com | https://plusonerobotics.sharepoint.com/:w:/r/sites/PlusOneDocumentation/POR TECHNICAL PUBLICATIONS LIBRARY/InductOne/V1 to V2 Retrofit Instructions/Conveyor Powered Roller Adjustment.docx?d=wd8846c11240b43d9ae0c7b463f8ea334&csf=1&web=1&e=DkbvbG | Completed |  | EC-25-203; needs to be made into ECR to added to assembly print.
Nov 6, 2025 | Denied | 8 | Nov 6, 2025 | James Nelson | james.nelson@plusonerobotics.com | Operations | Systems Engineer | Replace CMOS battery Beth SAI2-2 IPC2 CR2032 | Correct battery is BR2032. Battery in use is CR2032 because this is available as a consumer electronic part. Used until correct part is shipped. | Unbricks the IPCs CMOS memory (BIOS settings) in the interim. | UPS Bethlehem SAI 2-2 | Multiple sites for a specific project application | 2 | 3 |  | Anyone with clean, steady hands and an accessible grounded surface | Idk where the bios battery change article is but that. Flat head terminal screw driver, plus a screwdriver compatible with whatever screw the builder used to mount the IPC, and a phillips #1. |  |  | Nov 6, 2025 | patty.gomez@plusonerobotics.com |  | Cancelled |  | complete during manuf process? ECR not needed.
Nov 6, 2025 | In Progress | 9 | Nov 6, 2025 | James Nelson | james.nelson@plusonerobotics.com | Operations | Systems Engineer | Hose Changes at DHL Lane7 and 8, Onexia, Bethlehem SAI2-1 and Bethlehem SAI2-2 | Documenting hose lengths used in the field for the vacuum systems I have fixed/commissioned. | Robot doesn't smack the camera. Robot doesn't have a collision/HCAL/OVC every time it does PV recovery | All i1 | All future deployments for this customer | 1 | 1 | 0 | Anyone with 3 hands | 4mm allen wrench. Drawing needs to be fixed with below measurements. | see attached | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6382785654538525556/ECR%20Form%20Hose%20Clamp%20Positions.pdf https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6382785654538525556/image%20%288%29.png | Nov 6, 2025 | patty.gomez@plusonerobotics.com | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4326 | In Progress | https://gitlab.com/groups/plusone-robotics/product/-/work_items/849 | ecr created 12/22/25 per Shaun's request to validate if one is ready for released. epic created 12/23/25
Nov 7, 2025 | Complete | 10 | Nov 7, 2025 | James Nelson | james.nelson@plusonerobotics.com | Operations | Systems Engineer | i1 lights oriented straight down after OD retrofit | Lights used to be (v1) angled to reduce washout in the center of the FOV. With OD they need to be straight down. | OD Calibration repeatability, more even lighting generally. With the belt change, the ideal exposure decreased which makes the washout less common a higher lighting levels | All v2 i1, unclear if this is noted in the design documentation | All future deployments for this customer | 1 | 1 | 0 | Anyone that can use a socket wrench | None |  |  | Nov 7, 2025 | patty.gomez@plusonerobotics.com | https://plusonerobotics.sharepoint.com/:w:/r/sites/PlusOneDocumentation/POR%20TECHNICAL%20PUBLICATIONS%20LIBRARY/InductOne/V1%20to%20V2%20Retrofit%20Instructions/OD%20camera%20retrofit%20Instructions.docx?d=we09c8bf69139431bbc70134f0989d833&csf=1&web=1&e=c48Uvq | Completed |  | ECR completed
Nov 10, 2025 | Denied | 11 | Nov 10, 2025 | James Nelson | james.nelson@plusonerobotics.com | Operations | Systems Engineer | Beth2-1 Sidepan cutouts | The tolerance for our upstream sidepan interface (Upstream side of pickone conveyor side pan) is too tight to install without creating a jam or a hole. There is a change made on-site where the guard has a slot cut out to give space to accommodate bad installation/discrete placement options due to mezzanine grating. | Install without catch point or hole | UPS Beth SAI2-1 | One-time for a specific site | 2 | 2 | 0 | Unknown | Unknown. Just cutting 1/8" out of a section of the sidepan |  | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6385980801348662255/Image%20%282%29.jpg | Nov 10, 2025 | patty.gomez@plusonerobotics.com |  | Completed |  | ECR not needed
Nov 13, 2025 | In Progress | 12 | Nov 13, 2025 | Nathaniel Pantuso | nathaniel.pantuso@plusonerobotics.com | Customer Support | Operations Technician | v2 Gripper Retrofit - PSI specification change | The current documentation states to set the Festo regulator to 60psi but the golden unit has it set to 70psi. | Using 60psi causes a low pressure warning on the HMI and also displays red on the regulator. | All InductOne with v2 grippers | All future deployments for this application type | 0.5 | 0.5 | 0 | Anyone | updated guide. |  | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6388770512212286169/IMG3568_1762988642.jpg https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6388770512212286169/IMG3563_1762988648.jpg | Nov 13, 2025 | patty.gomez@plusonerobotics.com | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4327 | In Progress | https://gitlab.com/groups/plusone-robotics/product/-/work_items/850 | ecr created 12/22/25 per Shaun's request to validate if one is in progress. epic created 12/23/25
Dec 1, 2025 | In Progress | 13 | Dec 1, 2025 | James Nelson | james.nelson@plusonerobotics.com | Operations | Systems Engineer | Hose Changes at Onexia Cell 2 | Similar to before, pull forward the hose to add 3.5" of slack between J2 and the EOAT on Robot 2. (Documenting physical change made by Onexia) | Place area reachable | Onexia Cell 2, repeat as needed | Multiple sites for a specific project application | 0.5 | 0.5 | 0 | Anyone with 3 hands | 4mm allen and a dream | https://gitlab.com/plusone-robotics/operations/project_manager/builders/onexia/-/issues/3#note_2925543502 |  | Dec 1, 2025 | patty.gomez@plusonerobotics.com | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4326 | In Progress |  | added to item 8 ecr 12/22/25
Jan 7, 2026 | In Progress | 14 | Jan 7, 2026 | Wayne Kirk | wayne.kirk@plusonerobotics.com | Product | DesEng | Removal of Pump Enclosure Sound Insulation | This trip was prompted by an over-temperature situation with the pump enclosure. We believe the issue was a cascade of events leading to an elevated temperature within the pump enclosure. One possibility was the adhesive applied to the sound insulation failed (which has happened before), causing the sheets to fall onto the pump and over the ventilation fans. The pump's HOT air exhaust runs out of the enclosure normally though PVC fittings, which once exposed to the elevated enclosure temperatures softened and popped off of the pump leading to the dumping of that hot air into the enclosure. This caused a run-away thermal condition. Both ventilation fans failed. The proposed change is to omit the sound insulation material completely. | No longer having this insulation material in the panel avoids this thermal run-away condition. When the team (Moreno, Kirk, Gines) was on site in Bethlehem (Dec 16-17 2025) and removed the material, the sound of the pump running without it was not noticeable, let alone the sound level, since the ambient background noise in the facility if high. | UPS Bethlehem, UPS Worldport, future UPS sites, DHL DFW, future DHL DFW sites. | All future deployments for this application type | 1 | 1 |  | Technician | No tools. The adhesive peels away by hand. |  | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6436349202212009911/IMG_20251216_150116201_HDR.jpg | Jan 7, 2026 | patty.gomez@plusonerobotics.com | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4342 | ECR Submitted |  | ecr submitted 1/8/26.
Feb 2, 2026 | In Progress | 15 | Jan 21, 2026 | Patty Gomez | patty.gomez@plusonerobotics.com | Customer Support | Group Lead | Spacer to prevent R2 vac valve from rottatin | Under normal use, the vacuum valve on R2 rotates towards the canopy and will eventually crack the top filter cap off of the main valve body. The current temporary solution is to rotate the valve out/away from the canopy, 45 degrees; however, this requires periodic checks to ensure it has not rotated back towards the canopy. | Onexia has designed a spacer that prevents the valve body from rotating into the canopy. This was seen at the cell in Worldport. Request is to vet this solution and confirm we can implement moving forward. | All InductOne | All future deployments for this application type |  | 1.5 |  | Technician |  |  |  | Feb 2, 2026 |  | https://gitlab.com/groups/plusone-robotics/product/-/epics/861 | In Progress | https://gitlab.com/groups/plusone-robotics/product/-/epics/861 | ecr submitted 1/21/26.
Feb 2, 2026 | In Progress | 16 | Feb 2, 2026 | Patty Gomez | patty.gomez@plusonerobotics.com | Customer Support | Group Lead | Fan only part number request | When a fan fails, we do no need to typically replace the panel and filter portion, we can replace just the fan. However, we need a part number and vendor to order this as a standalone item. | Lower cost for fan only swap and quicker availability. Fan $436 Assembly: $774 | All InductOne | All future deployments for this application type | 1 | 1 | 436 | Technician |  | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4365 |  | Feb 2, 2026 | patty.gomez@plusonerobotics.com | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4365 | ECR Submitted |  | ecr submitted 2/2/26
Feb 2, 2026 | In Progress | 17 | Feb 2, 2026 | Patty Gomez | patty.gomez@plusonerobotics.com | Customer Support | Group Lead | Canister Filter part number request | We do not have the filter element on the BOM as a separate item available to sell/order. The part number we have listed is for a new canister with filter element; mcmaster-carr p/n: 5169K87, Vacuum-Rated Air-Intake Filter, 2 NPSC Female, 175 scfm for $403.92 each. | We can save on cost by selling just the filter as needed. mcmaster-carr p/n: 5169K93, 8-3/4" High Polyester Plastic Element for Vacuum-Rated Air-Intake Filter. 50.35 each. | All InductOne | All future deployments for this application type | 0.25 | 0.25 | 50.35 | Anyone | new filter |  |  | Feb 2, 2026 | patty.gomez@plusonerobotics.com | https://gitlab.com/plusone-robotics/product/issue_tracker/-/issues/4366 | ECR Submitted |  | ecr submitted 2/2/26.
Apr 6, 2026 | In Progress | 18 | Apr 6, 2026 | Jason Minica | jason.minica@plusonerobotics.com | Product | Team Lead | Beth 1-2 Field Test (grippers and vacuum hose) | Installation of redesigned grippers and two piece vacuum hoses for increased durability and longevity | Increased durability and longevity of these components | UPS Beth, cell 1-2 | One-time for a specific site |  |  |  | Mech Engineering | N/A | https://gitlab.com/groups/plusone-robotics/product/-/work_items/915 |  | Apr 6, 2026 | patty.gomez@plusonerobotics.com
Jul 8, 2026 | In Progress | 19 | Jul 8, 2026 | Chritinsa Gomez-Terry | christina.gt@plusonerobotics.com | Operations | VP of Operations | Fiber Network Install | Installed fiber-optic network configuration at the UPS Worldport IPC panel. UPS/Alliant added an Allen Bradley 1783-ETAP1F (unmanaged switch) for fiber-to-Ethernet conversion, powered from P8 of TB10025 (24V). A Corning fiber splicer was bolted directly to the IPC panel. No configuration steps were required on POR's side. | Original Ethernet cable run was too long and unreliable at the UPS Worldport facility. UPS installed fiber-optic infrastructure to provide stable OT network connectivity to the IPC panel | InductOne-WP UPS | One-time for a specific site |  |  |  | Electrical Contractor (Delta) under supervision of POR Operations | Fiber-optic cabling, Allen Bradley 1783-ETAP1F, Corning fiber splicer, standard electrician tools. Allen Bradley 1783-ETAP1F datasheet for power specifications. | https://gitlab.com/plusone-robotics/operations/project_manager/ups/worldport-inductone/-/work_items/170 | https://www.jotform.com/uploads/Patty_Gomez/252437610736154/6593483432218719404/FCO-2026-0129WP-UPS.docx | Jul 8, 2026 | patty.gomez@plusonerobotics.com
Jul 13, 2026 | In Progress | 20 | Jul 13, 2026 | Gilberto Bailey | gilbert.bailey@plusonerobotics.com | Operations | Sr. Systems Engineer | UPS Beth 2-2 Electrical Panel upgrade | Add 2 contactors to the MCP panel one for each robot. Rev E electrical diagrams have this change included. | Improvement: Automated robot power cycle to reset a major robot alarm that requires human intervention. | UPS | All future deployments for this application type | 8 | 8 | 600 | Anyone with a strong electrical background | - Contactors - Electrical wires - MCP Electrical diagrams - Basic wiring tools. | https://gitlab.com/plusone-robotics/operations/project_manager/ups/bethlehem-inductone/-/work_items/151. https://gitlab.com/plusone-robotics/product/hardware-engineering/robotic-induction-cells/inductone-dual-arm-induction/inductone-v2.0/-/work_items/296 |  | Jul 13, 2026 | patty.gomez@plusonerobotics.com